## Tasks
Task board: Programming Foundations project, Team B
How to use: tick the box in column A when a task is done. The filter arrows in row 5 show only your name or one week. Pull before you open the file; afterwards save, close Excel, commit and push.
Done: 3 of 33 tasks
Done | Week | Deadline | Who | Task | Kind | Notes
TRUE | CW 39 | 2026-09-27 | Team | Group registered on Moodle (Basel PT, Team B) | Course deadline
TRUE | CW 40 | 2026-09-30 | Team | Team repo created and everyone invited | Team target
TRUE | CW 40 | 2026-09-30 | Team | Problem statement and project goal written in ideas.md | Course deadline
FALSE | CW 41 | 2026-10-07 | Matteo | Write your 3 user stories and push them as "User Stories Matteo.md" | Course deadline | Format (S02 slides 22-24): "As a [role], I want to [capability], so that [benefit]", plus acceptance criteria and one Given-When-Then example.
FALSE | CW 41 | 2026-10-07 | Robert | Write your 3 user stories and push them as "User Stories Robert.md" | Course deadline | Format (S02 slides 22-24): "As a [role], I want to [capability], so that [benefit]", plus acceptance criteria and one Given-When-Then example.
FALSE | CW 41 | 2026-10-07 | Leroy | Write your 3 user stories and push them as "User Stories Leroy.md" | Course deadline | Format (S02 slides 22-24): "As a [role], I want to [capability], so that [benefit]", plus acceptance criteria and one Given-When-Then example.
FALSE | CW 41 | 2026-10-07 | Ahmed | Write your 3 user stories and push them as "User Stories Ahmed.md" | Course deadline | Format (S02 slides 22-24): "As a [role], I want to [capability], so that [benefit]", plus acceptance criteria and one Given-When-Then example.
FALSE | CW 41 | 2026-10-07 | Everyone | Read the other stories before class and check that no two people have the same one | Team target | Class starts at 13:15.
FALSE | CW 41 | 2026-10-07 | Team | Get the scope and all 12 user stories agreed by the lecturers | Course deadline | In class.
FALSE | CW 41 | 2026-10-07 | Team | Ask where the user stories are uploaded on Moodle | Team target | No upload activity was visible on 1 Oct.
FALSE | CW 41 | 2026-10-07 | Team | Ask whether the tkinter window in main.py is allowed | Team target | The guidelines ask for a command-line app that takes user input via the console.
FALSE | CW 41 | 2026-10-11 | Team | Topic and final, agreed user stories written down in the repo | Course deadline
FALSE | CW 41 | 2026-10-11 | Team | User stories uploaded to Moodle | Course deadline
FALSE | CW 42 | 2026-10-14 | Team | Split every user story into tasks, each with an owner | Team target
FALSE | CW 43 | 2026-10-21 | Team | Sketch the program flow and the function tree | Team target | What runs first, next and last. One job per function.
FALSE | CW 43 | 2026-10-21 | Team | Define input, processing and output | Team target | Including the files the app reads or writes and their format.
FALSE | CW 43 | 2026-10-21 | Team | Choose the data structures (list, tuple, set or dict) | Team target
FALSE | CW 43 | 2026-10-21 | Team | Core functions implemented and running | Course deadline
FALSE | CW 44-48 | 2026-12-02 | Matteo | Your 3 user stories implemented and pushed | Team target | Commit under your own GitHub account. No class in CW 45 (2 - 8 Nov).
FALSE | CW 44-48 | 2026-12-02 | Robert | Your 3 user stories implemented and pushed | Team target | Commit under your own GitHub account. No class in CW 45 (2 - 8 Nov).
FALSE | CW 44-48 | 2026-12-02 | Leroy | Your 3 user stories implemented and pushed | Team target | Commit under your own GitHub account. No class in CW 45 (2 - 8 Nov).
FALSE | CW 44-48 | 2026-12-02 | Ahmed | Your 3 user stories implemented and pushed | Team target | Commit under your own GitHub account. No class in CW 45 (2 - 8 Nov).
FALSE | CW 49 | 2026-12-02 | Team | Complete, working application | Course deadline | Project coaching in class: bring open questions.
FALSE | CW 49 | 2026-12-02 | Team | Check functionality against the assessment sheet (30 points) | Team target | Runs without errors, every promised feature works.
FALSE | CW 49 | 2026-12-02 | Team | Check the Python foundations against the assessment sheet (30 points) | Team target | Variables, data structures, if / for / while, functions.
FALSE | CW 49 | 2026-12-06 | Team | Every section of the README.md template filled in | Course deadline | Main functionality, project structure, how to run it.
FALSE | CW 49 | 2026-12-06 | Team | Each member's contribution stated in the documentation | Course deadline
FALSE | CW 49 | 2026-12-06 | Team | Slides for the 15-minute presentation | Team target | Why this topic, goals and features, project management, live demo.
FALSE | CW 49 | 2026-12-06 | Team | Repository set to public | Course deadline | Test the link in a private browser window.
FALSE | CW 49 | 2026-12-06 | Team | Slides exported as PDF with the link to the repository in them | Course deadline
FALSE | CW 49 | 2026-12-06 | Team | Hand in on Moodle: presentation PDF and Declaration of Originality | Course deadline | Deadline 23:55. Up to 72 hours late: grade capped at 4.0. Later: 1.0.
FALSE | CW 50-51 | 2026-12-09 | Everyone | Be ready to explain every line of your code | Course deadline | The Q&A has individual questions on your own user stories.
FALSE | CW 50-51 | 2026-12-09 | Team | Final presentation, 15 minutes plus Q&A | Course deadline | Wed 9 or 16 Dec, slot not announced yet.

## Deadlines
Deadlines at a glance
When | What
Wed 7 Oct, 13:15 | User stories ready for class, scope agreed with the lecturers
Sun 11 Oct | User stories defined (CW 41): in the repo and uploaded to Moodle
Wed 21 Oct | Program flow defined and core functions implemented (CW 43)
Wed 2 Dec | Complete, working application (CW 49, project coaching in class)
Sun 6 Dec, 23:55 | Hand in on Moodle. Up to 72 hours late: grade capped at 4.0. Later: 1.0
Wed 9 or 16 Dec | Final presentation, 15 minutes plus Q&A (slot not announced yet)
Source: semester programme and project guidelines (Guidelines_Projects_AS26.pdf). On the Tasks sheet these are marked "Course deadline"; "Team target" dates are our own.